## Sheet1
Name of Center: Center for Food Technology and Research (CEFTER)
Institution: Benue State University |  |  |  | On Schedule
Country: Nigeria
Center Leader: Dr. Barnabas Achakpa Ikyo |  |  |  | Behind Schedule
Annual Workplan (January-December, 2023)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2023 Y2Q1 |  |  | 2023 Y2Q2 |  |  | 2023 Y2Q3 |  |  | 2023 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 2 Institutional Impact
Sub-Action 2a: Regional/National Conference and Seminar by Staff and Students
Activity 1: Conduct needs assesment | Hold a meeting to consider modalities towards a national conference and seminar for Staff and Students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  |  |  |  | Centre Management
Activity 2: Organise national stakeholder workshop | Organise workshop for staff and students to come together and discuss problems of teaching, learning and research | [15 empty] | 20000 | 1500
Activity 3: Prepare report/proceedings and circulate | Prepare report/proceeding of the workshop and circulate | [15 empty] | 1000
Sub-Action 2b: National/Regional Post-harvest Clinic/activities
Activity 1: Conduct needs assesment | Consider improved techniques for food preservation and processing | Suggest new techniques | [12 empty] | Community members adopt improved techniques for food preservation and processing |  | 6000 |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee | Present considerations to technical committee for | [15 empty] | 1000
Activity 3: Identify Communities for participatory conduct of Post-Harvest Clinic | Consider the target prticipants from Regional and National communities for the Clinic | Make suggestions | [14 empty] | 8000
Activity 4: Design curriculum and train resource persons from the communities | Training of persons from different communities on post-harvest activities | Participate in trainings | [14 empty] | 15000
Action 2: DLI 3: Quantity of Students
Sub-Action 3a: Training of Farmers/Food handlers on safe hygiene and Transportation of Produce to Markets
Activity 1: Conduct needs assesment | Hold a meeting to set out modalities for the training | Participate in meetings | [12 empty] | Use of new modules by farmers/food handlers to improve their income |  |  |  |  | Centre Management
Activity 2: Prepare report and submit to Technical committee for consideration | Draft a report for the training and submit to Technical Committee | [15 empty] | 500
Activity 3: Organise Stakeholders' workshop for industries and local fabricators | Organise Stakeholders' workshop | Participate in workshop | [14 empty] | 1500
Activity 4: Identify suitable modules for safe transportation of fruits and vegetables, grains, roots and tubers | Identify modules that are suitable for the training | Suggest modules | [14 empty] | 500
Activity 5: Identify suitable communities to test run the modules | List out communities in which the modules will be tested | Suggest communities | [14 empty] | 500
Activity 6: Train community members in the use of developed modules | Community members will be trained in the use of the modules | Participate in trainings | [14 empty] | 7000 | 1000
Sub-Action 3b: Training of Technologist and Laboratory Automation
Activity 1: Conduct needs assesment to identify the areas of need | Identify the areas that require training of technologists | [13 empty] | Trained laboratory technologists deployed to the departments |  | 1000 |  |  | Centre Management
Activity 2: Conduct survey to identify national and international institutions with best training facilities | Consider available institutions with the best training facilities nationally and internationally | [15 empty] | 2000
Activity 3: Identify and send suitable candidates for training | Send candidates for training | Conduct trainings | [14 empty] | 35000
Sub-Action 3c: Student Recruitment
Activity 1: Advertise Senate approved programs on CEFTER website | Place application advert for on CEFTER website | [13 empty] | Students register and resume lectures |  | 1000 |  |  | Centre Management
Activity 2: Advertise Senate approved programs on local and regional print media | Advertise programs on local, regional and print media | [15 empty] | 5500
Activity 3: Technical committee meets to consider shortlisted candidates for admission | Shortlisting of qualified candidates for admission | [15 empty] | 1500
Activity 4: Postgraduate Board meets and approves admission list | Approval of admission list | [15 empty] | 1500
Sub-Action 3d: Student Support/Scholarships
Activity 1: Conduct needs assesment | Call for applications for Student Support/Scholarship | [13 empty] | Students receive support/scholarship letters |  |  |  |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship | Interested applicants apply for Support/Scholarship
Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students | Qualified students shortlisted for the award | [15 empty] | 2500
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval | Vice Chancellor considers the list for approval
Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis | Award of Support/scholarship | [15 empty] | 50000
Sub-Action 3e: Training of Students/Staff on use of ICT for learning
Activity 1: Conduct needs assessment | Conduct needs assessment | [13 empty] | Students and Staff using advanced software for their learning/teaching and research |  | 500 |  |  | Centre Management
Activity 2: Identify the software suitable for enhanced students learning | Identify suitable software for enhanced student learning | Suggest suitable software | [14 empty] | 500
Activity 3: Identify and engage a suitable resource person | Engage suitable resource persons | Suggest resource persons | [14 empty] | 1000
Activity 4: Organise training | Organise training sessions | [15 empty] | 6000
Action 4: DLI 4: Quality of Education/Research
Sub-Action 4a: CEFTER Thematic Annual Research Grant
Activity 1: Hold planning meetings | Hold meetings to plan and send out call for grant applications | [13 empty] | Annual Grant successfully awarded |  | 5000 |  |  | Centre Management
Activity 2: Receive and review grant applications | Review grant applications | Review applications | [14 empty] | 5000
Activity 3: Award grants to successful applicants | Award grants to applicants that meet the set criteria | [15 empty] | 70000
Sub-Action 4b: Funding peer reviewed publications from CEFTER Staff and Students
Activity 1: Students and faculty publications submitted to CEFTER publications committee | Publications by students and faculty submitted to committee for consideration | [13 empty] | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  |  |  | Centre Management
Activity 2: The committee reviews and shortlists good quality publications | Select quality publications | [15 empty] | 1000
Activity 3: Shortlisted publications sent to experts for peer review | Selected publications sent for review | [15 empty] | 1000
Activity 4: Payment of publication charges | Payment of publication charges | [15 empty] | 20000
Activity 5: Subscription to Journals | Subscription to Journals | [15 empty] | 4000
Sub-Action 4c: Construction of CEFTER Food Technology Innovation Complex (CEFTIC)
Activity 1: Installation and Finishing | Contract awarded for installation of Equipments | [15 empty] | 450000
Sub-Action 4d: Procurement of Laboratory Equipment and Consumables
Activity 1: Conduct needs assesment with departments and partners | Get a comprehensive list of equipments and consumables needed | [13 empty] | Students and Staff enjoying facilities procured for research and teaching |  |  |  |  | Centre Management
Activity 2: Draft report for consideration | Consider report
Activity 3: Submit Proposal to procurement committee | Submit proposal to procurement committee
Activity 4: Advertise for tenders | Advertise for tenders | [16 empty] | 1600
Activity 5: Contract awarded for purchase and installation (GCMS for Chemistry lab, FITR Spectrometer, Software and informatics) | Award contract | [15 empty] | 100000
Sub-Action 4e: Student-Faculty Grant (CPSS)
Activity 1: Students and faculty complete and submit application form | Call for and receive applications for grants from Sudents and Faculty | Submit applications | [12 empty] | Student and Faculty conducting research on approved projects |  |  |  |  | Centre Management
Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview | Cosider applications and shortlist candidates for interview | Participate in consideration of applications and shortlisting | [14 empty] | 1500
Activity 3: Shortlisted candidates defend their proposals before the committee | Proposal defence by shortlisted candidates | Proposal defence | [14 empty] | 1500
Activity 4: Disbursement to successful grant applicants | Successful candidates receive disbursement | [15 empty] | 35000
Activity 5: Special research grants | Successful candidates receive disbursement | [15 empty] | 12000
Sub-Action 4f: Establishment of Regional Research Groups
Activity 1: Conduct needs assesment for establishment of regional working groups | Hold meetings to consider available networking options and advantages | Participate in meetings | [12 empty] | Joint publications in high quality Journals |  | 4000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network | Organise workshops to form regional groups and consider networking options | Participate in workshops | [14 empty] | 14000
Activity 3: Draft reports and share | Draft and share reports | [15 empty] | 2000
Sub-Action 4g: Training on research proposals and publication writing
Activity 1: Prepare report for consideration |  | Participate in meetings | [12 empty] | Publications in high quality Journals |  | 1000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Identify Facilitators and Benefiaries |  | Participate in workshops | [14 empty] | 2000
Activity 3: Implement training | [16 empty] | 10000
Sub-Action 4h: International/National Program Accreditation
Activity 1: Identify Accreditation body and university programs for accreditation | Consider the university programs that will be pushed for accreditation, consider and contact the accreditation body that will be engaged for the process | Participate in meetings | [12 empty] | Publications in high quality Journals |  | 1000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Commencement of the process for accreditation | Direct HODs to put together all required paperworks for invitation | Participate in workshops | [14 empty] | 3000
Activity 3: Undergo process for full accreditation | The accreditation process fully implemented | [15 empty] | 56000
Action 5: DLI 5: Relevance of Education/Research
Sub-Action 5a: Partnership Activities
Activity 1: Training of Staff at MSc, PhD levels: Study fellowship | Staff considered for study fellowship | Train Staff at MSc and PhD levels | [12 empty] | Completion of agreed activities for each quater |  | 25000 |  |  | Project Technical Committee
Activity 2: Student Internships (This includes accomodation, monthly stipend, transport, supervision and consumables) | Students engaged on internships | Organise internships | [14 empty] | 20000
Activity 3: Joint Projects | Joint activities with partners | Jiont activities | [14 empty] | 20000
Activity 4: Short courses training: Local and international travels | Local and international participation in short courses | Participation in short courses | [14 empty] | 20000 | 14000
Activity 5: Refurbishing of partnership offices | Renovation and furnishing of some partnership offices | [15 empty] | 15000
Sub-Action 5b: Faculty and Students Food Post-harvest Week
Activity 1: Conduct needs assesment | Formulate student groups | [13 empty] | Students and Entrepreneurs establish businesses using processed food products. Successful patentingof some food products |  |  |  |  | Centre Management
Activity 2: Identify crops and assign to students groups | Assign specific crops to student groups | [15 empty] | 1000
Activity 3: Assign faculty to student groups as mentor | Assign faculty to each student group to serve as mentor
Activity 4: Student identify food products and prepare budgets | Students prepare and submit budgets | [15 empty] | 2000
Activity 5: Funding | Funds released for raw materials and accessories for the food week | [15 empty] | 10000
Sub-Action 5c: CEFTER Enterprise Development
Activity 1: Hold planning meetings | Call for applications on enterprise development | [13 empty] | One startup per year |  | 1000 |  |  | Centre Management
Activity 2: Receive and review applications | Review submitted applications | Review applications | [14 empty] | 5000
Activity 3: Setup small and medium scale Funding for three year start-ups per year. 10 winning groups in the enterprise competition will use the fund to set up an agro based small scale enterprise | Consider successful applications for small and medium scale funding for start-ups | Consider applications | [14 empty] | 65000
Sub-Action 5d: Provision of Extension and Community Awarness on Post-Harvest Losses
Activity 1: Create digital database on agricultural produce | There will be a digital database to promote effectiveness | Participate in meetings | [12 empty] | Members of the Community adopt improved processing and preservation techniques |  | 1000 |  |  | Centre Management
Activity 2: Update and review data | Data will be collected from the field extension staff at regular basis to update the database | Participate in meetings | [14 empty] | 1000 |  |  | Centre Management
Activity 3: Training of additional extension workers | In addition to those trained, the Centre will conduct a training to expand on the existing numbers
Activity 4: Organise yearly community awareness campaigns in selected countries in West and Central Africa | Organise awarenesses campaigns | Engage in campaigns | [14 empty] | 5000 |  |  | CentreManagement
Activity 5: Implementation of the extension service network | Fund and support networks for agricultual extension services | Suggest specific areas and locations | [14 empty] | 6000 |  |  | and Partners
Sub-Action 5e: Student Internship
Activity 1: Identify Industrial and sectoral Partners for students' internship | Identify the Industries and Sectoral partners that can meet the internship needs | Identify industries and partners | [14 empty] | 1000
Activity 2: Consider internship areas | Consider the different areas for students internships | Present internship areas | [17 empty] | Centre Management
Activity 3: Develop internship manuals | Develop manuals for internship | Develop manuals | [14 empty] | 1000
Activity 4: Develop Schedule for Student distribution | Prepare a student distribution schedule
Activity 5: Payment of intern service charges at industrial site | Payment of intern service charges at industrial site | [15 empty] | 38000
Sub-Action 5g: Grant Application:
Activity 1: Hold planning meetings | Hold meetings and consider available grants | Suggest grant winning ideas | [12 empty] | 3 grants applications submitted each year |  | 2000 |  |  | Centre Management
Activity 2: Write and apply for grants | Apply for grants | Facilitate applications | [14 empty] | 8000
Action 6: DLI 6: Timeliness/Quality of Financial Management
Sub-Action 6a: Regional Project Review Workshops
Activity 1: Identify and notify participants | Identify and notify regional workshop participants | [13 empty] | Management identifying areas of weakness for improvement |  | 1500 |  |  | Centre Management
Activity 2: Prepare update report on project | Prepare update report on project | [15 empty] | 1000
Activity 3: Submit to CEFTER technical Committee for inputs | Submit report to technical committee for consideration | [15 empty] | 1000
Activity 4: Travels and accomodation cost | Settle workshop expenses | [15 empty] | 31500
Sub-Action 6b: Internal Monitoring and Evaluation Activities
Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines | Review CEFTER activities quaterly | [15 empty] | 5000 |  |  | M&E team
Sub-Action 6c: Maintenance of ICT Facilities at the new Postgraduate Centre
Activity 1: Maintenance of installation | Maintenance of facilities installed | [15 empty] | 5000 |  |  | Centre Management
Sub-Action 6d: Financial Management
Activity 1: Meeting of Audit committee | The audit committee meets to consider financial reports | [15 empty] | 1500 |  |  | Audit Committee
Activity 2: Training of account/audit staff | Account/Audit staff shall attend annual trainings and workshops | [15 empty] | 20000 |  |  | Centre Management
Activity 3: Purchace and update of accounting software | Payment for licences and upgrade of software | [15 empty] | 3000 |  |  | Accounts Unit
Activity 4: External Audit | External audit of financial reports | [15 empty] | 5000 |  |  | External Auditor
Action 7: DLI : Institutional Impact
Sub-Action 7a: International Institutional Accreditation
Activity 1: Get approval of AAU for a proposed international accrediting body | The AAU must approve accrediting body prior to beginning the accreditation process | [13 empty] | Letter from accrediting body confirming fulfullment of full institutional accreditation |  | 5000 |  |  | Centre Management
Activity 2: Commencement of the process for self study and GAP assessment | Direct engagement with the international accrediting body to undertake either self-study or gap assessment | [15 empty] | 15000
Activity 3: Undergo processes for full international accreditation | The institution will undergo international accreditation with the approved accrediting body following the completion of the self evaluation/gap assesment. | [15 empty] | 60000
Sub-Action 7b: Second Round of Institutional benchmarking (PASET)
Activity 1: Meeting milestones for promoting institutional Impact as outlined in Implimentation Plan | [14 empty] | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise |  | 5000 |  |  | Centre Management
Action 8: Communication
Activity 1: Regular Website updates | As part of DLI 1, each centre developed a website to further project its activities. Centres should ensure links to their websites are active. Regularly update website with news, originally generated articles, success stories, alumni/student focused articles, stories written from research works etc. (new posts should not only be about calls for applications and upcoming events). These should also be regularly shared with the ACE Impact Communications team at the AAU. Improve website interface (design and navigation) | [13 empty] | Active website links |  | 2000
Activity 2: Regular update of social media platforms | [14 empty] | Minimum of 3 posts weekly |  | 5000
Activity 3: Online repository for research outputs | Communicate the research outputs of studies conducted by the centres and make it easy for stakeholders to access them. | [13 empty] | Visible page/ tab on centre’s website outlining the various research undertaken by the centre. |  | 3000
Activity 4: Media engagement | Engage mainstream media to further disseminate centre’s output/ success stories- sharing compelling articles with local and international media. | [13 empty] | At least 1 mainstream feature quarterly |  | 5000
Activity 5: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Produce newsletters and magazines. Theatre Arts department will be engaged to produce TV and radio jingles that highlight success stories, key activities, and events of the centre in various local languages. They will also be at the forefront of descemination of information. Produce simple communication materials such as brochures and factsheets. | [13 empty] | Production of quarterly/ bi-annual newsletters |  | 5000
Activity 6: Produce and Circulate flyers, Posters and Monographs | [16 empty] | 3000
[15 empty] | TOTAL |  | 1397500
[16 empty] | Total Estimated Budget ($) | 1397500