## General Work Plan
COUNTRY: NIGERIA
PROJECT NAME: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE NAME: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH WORK PLAN (JANUARY - DECEMBER 2023)
Year 2023
Activity No | ACTIVITY | SUB-ACTIVITY | JUSTIFICATION | ESTIMATED BUDGET ($) | REMARKS | RESPONSIBLE UNIT
[7 empty] | January | February | March | April | May | June | July | August | September | October | November | December
1.1 | Regional/National Conference and Seminar by Staff and Students | Activity 1: Conduct needs assesment | Mainstreaming of improved learning and teaching methods in the institutions |  |  | Centre Management
|  | Activity 2: Organise national stakeholder workshop |  | 20000
|  | Activity 3: Prepare report/proceedings and circulate |  | 1000
1.2 | National/Regional Post-harvest Clinic/activities | Activity 1: Conduct needs assesment | Community members adopt improved techniques for food preservation and processing | 6000 |  | Centre Management
|  | Activity 2: Draft report for consideration by Technical Committee |  | 1000
|  | Activity 3: Identify Communities for participatory conduct of Post-Harvest Clinic |  | 8000
|  | Activity 4: Design curriculum and train resource persons from the communities |  | 15000
2.1 | Training of Farmers/Food handlers on safe hygiene and Transportation of Produce to Markets | Activity 1: Conduct needs assesment | Use of new modules by farmers to improve their income. |  |  | Centre Management
|  | Activity 2: Prepare report and submit to Technical committee for consideration |  | 500
|  | Activity 3: Organise Stakeholders' workshop for industries and local fabricators |  | 1500
|  | Activity 4: Identify suitable modules for safe transportation of fruits and vegetables, grains, roots and tubers |  | 500
|  | Activity 5: Identify suitable communities to test run the modules |  | 500
|  | Activity 6: Train community members in the use of developed modules |  | 7000
2.2 | Training of Technologist and Laboratory Automation | Activity 1: Conduct needs assesment to identify the areas of need | Trained laboratory technologists deployed to the departments | 1000 |  | Centre Management
|  | Activity 2: Conduct survey to identify national and international institutions with best training facilities |  | 2000
|  | Activity 3: Identify and send suitable candidates for training |  | 35000
2.3 | Student Recruitment | Activity 1: Advertise Senate approved programs on CEFTER website | Students register and resume lectures | 1000 |  | Centre Management
|  | Activity 2: Advertise Senate approved programs on local and regional print media |  | 5500
|  | Activity 3: Technical committee meets to consider shortlisted candidates for admission |  | 1500
|  | Activity 4: Postgraduate Board meets and approves admission list |  | 1500
2.4 | Student Support/Scholarships | Activity 1: Conduct needs assesment | Students receive support/scholarship letters |  |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship
|  | Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students |  | 2500
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval
|  | Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis |  | 50000
2.5 | Training of Students/Staff on use of ICT for learning | Activity 1: Conduct needs assessment | Students and Staff will use advanced software for their learning/teaching and research | 500 |  | Centre Management
|  | Activity 2: Identify the software suitable for enhanced students learning |  | 500
|  | Activity 3: Identify and engage a suitable resource person |  | 1000
|  | Activity 4: Organise training |  | 6000
3.1 | CEFTER Thematic Annual Research Grant | Activity 1: Hold planning meetings | Annual Grant successfully awarded | 5000 |  | Centre Management
|  | Activity 2: Receive and review applications |  | 5000
|  | Activity 3: Award grants |  | 70000
3.2 | Funding Peer Reviewed publications from CEFTER Staff and Students | Activity 1: Students and faculty publications submitted to CEFTER publications committee | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  | Centre Management
|  | Activity 2: The committee reviews and shortlists good quality publications |  | 1000
|  | Activity 3: Shortlisted publications sent to experts for peer review |  | 1000
|  | Activity 4: Payment of publication charges |  | 20000
|  | Activity 5: Subscription to Journals |  | 4000
3.3 | Construction of CEFTER Food Technology Innovation Complex (CEFTIC) | Activity 1: Installation and Finishing |  | 450000
3.4 | Procurement of Laboratory Equipment and Consumables | Activity 1: Conduct needs assesment with departments and partners | Students and Staff enjoying facilities procured for research and teaching |  |  | Centre Management
Activity 2: Draft report for consideration
Activity 3: Submit Proposal to procurement committee
Activity 4: Advertise for tenders
|  | Activity 5: Contract awarded for purchase and installation (GCMS for Chemistry lab, FITR Spectrometer, Software and informatics) |  | 100000
3.5 | Student-Faculty Grant (CPSS) | Activity 1: Students and faculty complete and submit application form | Student and Faculty conducting research on approved projects |  |  | Centre Management
|  | Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview |  | 1500
|  | Activity 3: Shortlisted candidates defend their proposals before the committee |  | 1500
|  | Activity 4: Disbursement to successful grant applicants |  | 35000
|  | Activity 5: Special research grants |  | 12000
3.6 | Establishment of Regional Research Groups | Activity 1: Conduct needs assesment for establishment of regional working groups | Joint publications in high quality Journals | 4000 |  | Centre Management
|  | Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network |  | 14000
|  | Activity 3: Draft reports and share |  | 2000
3.7 | Training on research proposals and publication writing | Activity 1: Prepare report for consideration | Publications in high quality Journals | 1000 |  | Centre Management
|  | Activity 2: Identify Facilitators and Benefiaries |  | 2000
|  | Activity 3: Implement training |  | 10000
3.8 | International/National Program Accreditation | Activity 1: Identify Accreditation body and university programs for accreditation | Publications in high quality Journals | 1000 |  | Centre Management
|  | Activity 2: Commencement of the process for accreditation |  | 3000
|  | Activity 3: Undergo process for full accreditation |  | 56000
4.1 | Partnership Activities | Activity 1: Training of Staff at MSc, PhD levels: Study fellowship | Completion of agreed activities for each quater | 25000 |  | Centre Management
|  | Activity 2: Student Internships (This includes accomodation, monthly stipend, transport, supervision and consumables) |  | 20000
|  | Activity 3: Joint Projects |  | 20000
|  | Activity 4: Short courses training: Local and international travels |  | 20000
|  | Activity 5: Refurbishing of partnership offices |  | 15000
4.2 | Faculty and Students Food Post-harvest Week | Activity 1: Conduct needs assesment | Students and Entrepreneurs establish businesses using processed food products. Successful patentingof some food products |  |  | Centre Management
|  | Activity 2: Identify crops and assign to students groups |  | 1000
Activity 3: Assign faculty to student groups as mentor
|  | Activity 4: Student identify food products and prepare budgets |  | 2000
|  | Activity 5: Funding |  | 10000
4.3 | CEFTER Enterprise Development | Activity 1: Hold planning meetings | One startup per year | 1000 |  | Centre Management
|  | Activity 2: Receive and review applications |  | 5000
|  | Activity 3: Setup small and medium scale Funding for three year start-ups per year. 10 winning groups in the enterprise competition will use the fund to set up an agro based small scale enterprise |  | 65000
4.4 | Provision of Extension and Community Awarness on Post-Harvest Losses | Activity 1: Create digital database on agricultural produce | Members of the Community adopt improved processing and preservation techniques | 1000 |  | Centre Management and Partners
|  | Activity 2: Update and review data |  | 1000
Activity 3: Training of additional extension workers
|  | Activity 4: Organise yearly community awareness campaigns in selected countries in West and Central Africa |  | 5000
|  | Activity 5: Implementation of the extension service network |  | 6000
4.5 | Student Internship | Activity 1: Identify Industrial and sectoral Partners for students' internship |  | 1000 |  | Centre Management
Activity 2: Consider internship areas
|  | Activity 3: Develop internship manuals |  | 1000
Activity 4: Develop Schedule for Student distribution
|  | Activity 5: Payment of intern service charges at industrial site |  | 38000
4.6 | Grant Application: | Activity 1: Hold planning meetings | 3 grants applications submitted each year | 2000 |  | Centre Management
|  | Activity 2: Write and apply for grants |  | 8000
5.1 | Regional Project Review Workshops | Activity 1: Identify and notify participants | Management identifying areas of weakness for improvement | 1500 |  | Centre Management
|  | Activity 2: Prepare update report on project |  | 1000
|  | Activity 3: Submit to CEFTER technical Committee for inputs |  | 1000
|  | Activity 4: Travels and accomodation cost |  | 31500
5.2 | Internal Monitoring and Evaluation Activities | Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines |  | 5000 |  | M&E team
5.3 | Maintenance of ICT Facilities at the new Postgraduate Centre | Activity 1: Maintenance of installation |  | 5000 |  | Centre Management
5.4 | Financial Management | Activity 1: Meeting of Audit committee |  | 1500 |  | Audit Committee
|  | Activity 2: Training of account/audit staff |  | 20000 |  | Centre Management
|  | Activity 3: Purchace and update of accounting software |  | 3000 |  | Accounts Unit
|  | Activity 4: External Audit |  | 5000 |  | External Auditor
6.1 | International Institutional Accreditation | Activity 1: Get approval of AAU for a proposed international accrediting body | Letter from accrediting body confirming fulfullment of full institutional accreditation | 5000 |  | Centre Management
|  | Activity 2: Commencement of the process for self study and GAP assessment |  | 15000
|  | Activity 3: Undergo processes for full international accreditation |  | 60000
6.2 | Second Round of Institutional benchmarking (PASET) | Activity 1: Meeting milestones for promoting institutional Impact as outlined in Implimentation Plan | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise | 5000 |  | Centre Management
7.1 | Communication | Activity 1: Regular Website updates | Active website links | 2000
|  | Activity 2: Regular update of social media platforms | Minimum of 3 posts weekly | 5000
|  | Activity 3: Online repository for research outputs | Visible page/ tab on centre’s website outlining the various research undertaken by the centre. | 3000
|  | Activity 4: Media engagement | At least 1 mainstream feature quarterly | 5000
|  | Activity 5: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Production of quarterly/ bi-annual newsletters | 5000
|  | Activity 6: Produce and Circulate flyers, Posters and Monographs |  | 3000
| Total |  |  | 1397500
| Operating Expenses 10% |  |  | 139750
| Grand Total |  |  | 1537250

## Procurement Plan Works
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
WORKS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦411= U.S. $1.00

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
Loan No
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
1 | Procurement of Laboratory Equipment and Consumables |  |  | 100000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2023-01-23 | 2023-01-30 | 2023-02-06 | NA |  | 100000 | 2023-02-13 |  | 2023-02-20 |  | 2023-03-06
2 | Installation and Finishing for CEFTER food Technology Innovation Complex (CEFTIC) |  |  | 450000 | RFQ | Post Qualification | Post Review |  |  | NA |  | 2023-03-06 | 2023-03-20 | 2023-04-17 | NA |  | 450000 | 2023-04-24 |  | 2023-05-08 |  | 2023-05-29
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Total Cost |  |  | 550000 | [12 empty] | 550000
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦411= U.S. $1.00

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO:
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
For Contracts under projects approved before the May 2002 Guidelines
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | Description* | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
| Norm Duration of Proc Steps |  |  |  |  | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
List of Contracts
1 | National/Regional Post-harvest Clinic/activities | DIR |  | 30000 | Prior R | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | DIR | TIME BASE |  |  | Actual | [6 empty] | Actual | 2023-05-01 | 2023-05-15 | 2023-06-05 | NA | NA |  |  | Actual |  |  | 30000 | 2023-07-03 |  | 2023-07-10 | Actual |  |  |  | 50000
2 | International/National Program Accreditation | CD |  | 60000 | Prior R | Plan |  | NA | NA | NA |  |  | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | CD | TIME BASE |  |  | Actual | [6 empty] | Actual | 2023-05-01 | 2023-05-15 | 2023-06-05 |  |  |  |  | Actual | NA | NA | 60000 | 2023-07-03 | NA | 2023-07-10 | Actual |  |  |  | 60000
3 | International Institutional Accreditation | PPP |  | 80000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | PPP | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | 2023-01-09 | NA | 2023-01-16 |  |  |  |  | Actual | NA | NA | 80000 | NA | NA | NA | Actual |  |  |  | 95000
4 | Communication | DIR |  | 23000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | DIR | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | NA | NA | NA |  |  |  |  | Actual | NA | NA | 23000 | NA | NA | NA | Actual |  |  |  | 63000
5 | CEFTER Enterprise Development | PPP |  | 71000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
|  | PPP | TIME BASE |  | Prior R | Actual |  | NA | NA | NA |  |  | Actual | NA | NA | NA |  |  |  |  | Actual | NA | NA | 71000 |  | NA |  | Actual |  |  |  | 175000
| TOTAL AMOUNT |  |  | 264000 |  | Plan | [6 empty] | Plan | [7 empty] | Plan | [6 empty] | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual

## Procurement Plan Training
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CREDIT NO: IDA
NAME OF INSTITUTION: BENUE STATE UNIVERSITY MAKURDI
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | Training of Farmers/Food handlers on safe hygiene and Transportation of Produce to Markets | farmers/food handlers/resource persons | use of new modules by formers to improve their income | sustainable use of safe and hygienic transportation modules for produce to markets |  | 10000
2 | Training of Technologist and Laboratory Automation | Laboratory and Technologist staff | Students benefitting from new innovative teaching methods. Increase in number of faculty using innovative teaching methods | Curricula for innovative University teaching developed |  | 38000
3 | Training of Students/Staff on use of ICT for learning | staff | Generation of high quality technologist and laboratory automation personnel | Qualified candidates identified |  | 8000
4 | Training on research proposals and publication writing | staff/students | Students and staff using advanced software for their learning/teaching and research | Students and staff equipped for active learning |  | 13000
[5 empty] | TOTAL | 69000

## Disbursement Plan
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE FOR DEVELOPMENT IMPACT (ACE IMPACT)
CENTRE: CENTRE FOR FOOD TECHNOLOGY AND RESEARCH
CREDIT NO: IDA
DISBURSEMENT PLAN (JANURY - DECEMBER, 2023)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 |  | Procurement of Laboratory Equipment and Consumables | AMOUNT $: 100000; MONTHS JAN: 100000; MONTHS TOTAL: 100000
2 |  | Installation and Finishing for CEFTER food Technology Innovation Complex (CEFTIC) | AMOUNT $: 450000; MONTHS MAR: 450000; MONTHS TOTAL: 450000
3 |  |  | MONTHS TOTAL: 0
4 |  |  | MONTHS TOTAL: 0
5 |  |  | MONTHS TOTAL: 0
TRAINING
1 |  | Training of Farmers/Food handlers on safe hygiene and Transportation of Produce to Markets | AMOUNT $: 10000; MONTHS JAN: 10000; MONTHS TOTAL: 10000
2 |  | Training of Technologist and Laboratory Automation | AMOUNT $: 38000; MONTHS APR: 38000; MONTHS TOTAL: 38000
3 |  | Training of Students/Staff on use of ICT for learning | AMOUNT $: 8000; MONTHS OCT: 8000; MONTHS TOTAL: 8000
4 |  | Training on research proposals and publication writing | AMOUNT $: 13000; MONTHS JUL: 13000; MONTHS TOTAL: 13000
CONSULTANCIES
1 |  | National/Regional Post-harvest Clinic/activities | AMOUNT $: 30000; MONTHS JUL: 30000; MONTHS TOTAL: 30000
2 |  | International/National Program Accreditation | AMOUNT $: 60000; MONTHS JUL: 60000; MONTHS TOTAL: 60000
3 |  | International Institutional Accreditation | AMOUNT $: 80000; MONTHS JAN: 80000; MONTHS TOTAL: 80000
4 |  | Communication | AMOUNT $: 23000; MONTHS JAN: 23000; MONTHS TOTAL: 23000
5 |  | CEFTER Enterprise Development | AMOUNT $: 71000; MONTHS APR: 71000; MONTHS TOTAL: 71000
6
OPERATING COST
1 |  | Regional/National Conference and Seminar by Staff and Students | AMOUNT $: 21000; MONTHS JAN: 11000; MONTHS JUL: 10000; MONTHS TOTAL: 21000
2 |  | Student Recruitment | AMOUNT $: 9500; MONTHS JAN: 9500; MONTHS TOTAL: 9500
3 |  | Student Support/Scholarships | AMOUNT $: 52500; MONTHS JUL: 52500; MONTHS TOTAL: 52500
4 |  | CEFTER Thematic Annual Research Grant | AMOUNT $: 80000; MONTHS APR: 80000; MONTHS TOTAL: 80000
5 |  | Funding Peer Reviewed publications from CEFTER Staff and Students | AMOUNT $: 26000; MONTHS JAN: 16000; MONTHS JUL: 10000; MONTHS TOTAL: 26000
6 |  | Student-Faculty Grant (CPSS) | AMOUNT $: 50000; MONTHS JAN: 20000; MONTHS JUL: 15000; MONTHS OCT: 15000; MONTHS TOTAL: 50000
7 |  | Establishment of Regional Research Groups | AMOUNT $: 20000; MONTHS JUL: 20000; MONTHS TOTAL: 20000
8 |  | Partnership Activities | AMOUNT $: 100000; MONTHS JAN: 20000; MONTHS MAR: 20000; MONTHS MAY: 20000; MONTHS JUL: 20000; MONTHS SEP: 10000; MONTHS NOV: 10000; MONTHS TOTAL: 100000
9 |  | Faculty and Students Food Post-harvest Week | AMOUNT $: 13000; MONTHS APR: 13000; MONTHS TOTAL: 13000
10 |  | Provision of Extension and Community Awarness on Post-Harvest Losses | AMOUNT $: 13000; MONTHS MAR: 5000; MONTHS JUN: 3000; MONTHS SEP: 5000; MONTHS TOTAL: 13000
11 |  | Student Internship | AMOUNT $: 40000; MONTHS MAY: 40000; MONTHS TOTAL: 40000
12 |  | Grant Application: | AMOUNT $: 10000; MONTHS FEB: 4000; MONTHS MAY: 4000; MONTHS SEP: 2000; MONTHS TOTAL: 10000
13 |  | Regional Project Review Workshops | AMOUNT $: 35000; MONTHS MAR: 20000; MONTHS AUG: 15000; MONTHS TOTAL: 35000
14 |  | Internal Monitoring and Evaluation Activities | AMOUNT $: 5000; MONTHS JAN: 1000; MONTHS MAR: 1000; MONTHS MAY: 1000; MONTHS JUL: 1000; MONTHS SEP: 1000; MONTHS TOTAL: 5000
15 |  | Maintenance of ICT Facilities at the new Postgraduate Centre | AMOUNT $: 5000; MONTHS FEB: 2000; MONTHS JUL: 2000; MONTHS SEP: 1000; MONTHS TOTAL: 5000
16 |  | Financial Management | AMOUNT $: 29500; MONTHS MAR: 9000; MONTHS JUN: 9000; MONTHS AUG: 7000; MONTHS OCT: 4500; MONTHS TOTAL: 29500
17 |  | Second Round of Institutional benchmarking (PASET) | AMOUNT $: 5000; MONTHS JAN: 5000; MONTHS TOTAL: 5000
18 |  |  | MONTHS TOTAL: 0
19 |  |  | MONTHS TOTAL: 0
20 |  |  | MONTHS TOTAL: 0
21 |  |  | MONTHS TOTAL: 0
22 |  |  | MONTHS TOTAL: 0
23 |  |  | MONTHS TOTAL: 0
24 |  |  | MONTHS TOTAL: 0
25 |  |  | MONTHS TOTAL: 0
26 |  |  | MONTHS TOTAL: 0
27 |  |  | MONTHS TOTAL: 0
28 |  |  | MONTHS TOTAL: 0
0
| TOTAL |  | 1397500 | 295500 | 6000 | 505000 | 202000 | 65000 | 12000 | 233500 | 22000 | 19000 | 27500 | 10000 | 0 | 1397500