## Sheet1
Name of Center: Center for Food Technology and Research (CEFTER)
Institution: Benue State University |  |  |  | On Schedule
Country: Nigeria
Center Leader: Dr. Barnabas Achakpa Ikyo |  |  |  | Behind Schedule
Annual Workplan (January-December, 2024)
Work Plan Activities | Description | Partner Contribution (if relevant) | 2024 Y2Q1 |  |  | 2024 Y2Q2 |  |  | 2024 Y2Q3 |  |  | 2024 Y2Q4 |  |  | Milestone/Output | If NEW, Provide Justification | Estimated Budget($) | Estimated Revenue ($) | Contribution from Partner ($) | Person Responsible
|  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Action 1: DLI 2 Institutional Impact
Sub-Action 2a: Regional/National Conference and Seminar by Staff and Students
Activity 1: Collaboration with FOOD4WA on ongoing Regional seminar series | Review of Seminar presentations and coordination of participation by staff and Students | [13 empty] | Mainstreaming of improved learning and teaching methods in the institutions |  | 2000 |  |  | Centre Management
Activity 2: Organise virtual West Africa post Harvest Congress | Organise a virtual conference, presentations and poster sessions | [15 empty] | 10000 | 1500
Activity 3: Prepare report/proceedings and circulate | Prepare report/proceeding of the workshop and circulate | [15 empty] | 2000
Activity 4: Sponsorship of staff and students on regional/national/international conference | Sponsor a minimum of 3 staff on conferences | [15 empty] | 20000
Sub-Action 2b: Post-harvest Clinic/activities
Activity 1: Conduct needs assesment to identify Communities for participatory conduct of Post-Harvest Clinic | Identify Communities for participatory conduct of Post-Harvest Clinic | Suggest new techniques | [12 empty] | Community members adopt improved techniques for food preservation and processing |  | 1000 |  |  | Centre Management
Activity 2: Draft report for consideration by Technical Committee | Present considerations to technical committee for | [15 empty] | 1000
Activity 3: Design curriculum and train resource persons from the communities | Training of persons from different communities | Participate in trainings | [14 empty] | 10000
Action 2: DLI 3: Quantity of Students
Sub-Action 3a: Implementation of modules developed from the training on transportation of foodproduce to market, food handling, processing and preservation
Activity 1: Identify suitable individuals/communities to test run the modules | Hold a meeting to set out modalities for the training | Participate in meetings | [12 empty] | Use of new modules by farmers/food handlers to improve their income |  | 1000 |  |  | Centre Management
Activity 2: Train community members in the use of developed modules | Identify modules that are suitable for the training | Suggest modules | [14 empty] | 10000
Sub-Action 3b: Training of Technologist and Laboratory staff on more specialised equipment
Activity 1: Identify the new specialised equipment and conduct training | Identify the new specialised equipment and conduct training | [13 empty] | Trained laboratory technologists deployed to the departments |  | 2000 |  |  | Centre Management
Activity 2: Payment for softwares, licence subscriptions | Payment for softwares, licence subscriptions | [15 empty] | 10000
Activity 3: Identify and send suitable candidates for training | Send candidates for training | Conduct trainings | [14 empty] | 10000
Sub-Action 3c: Student Recruitment
Activity 1: Advertise Senate approved programs online. | Place application advert for on CEFTER website | [13 empty] | Students register and resume lectures |  | 500 |  |  | Centre Management
Activity 2: Advertise Senate approved programs on local and regional print media | Advertise programs on local, regional and print media | [15 empty] | 1500
Activity 3: Technical committee meets to consider shortlisted candidates for admission | Shortlisting of qualified candidates for admission. Targets: PhD - 20, Masters - 40
Activity 4: Postgraduate Board meets and approves admission list | Approval of admission list | [15 empty] | 1000
Sub-Action 3d: Student Support/Scholarships
Activity 1: Call for scholarship applications | Call for applications for Student Support/Scholarship | [13 empty] | Students receive support/scholarship letters |  |  |  |  | Centre Management
Activity 2: Students Complete application forms seeking for support/scholarship | Interested applicants apply for Support/Scholarship
Activity 3: CEFTER Scholarship and Grants Allocation Committee meets to Shortlist qualified students | Qualified students shortlisted for the award | [15 empty] | 2500
Activity 4: Shortlisted students forwarded to the Vice Chancellor for Approval | Vice Chancellor considers the list for approval
Activity 5: Funding for scholarship awarded to students annually. Covers tuition, accommodation and living expensis | Award of Support/scholarship (Funding for 50 students) | [15 empty] | 50000
Sub-Action 3e: Training of Students/Staff on use of ICT for learning
Activity 1: Identify the software suitable for enhanced students learning | Identify suitable software for enhanced student learning | [13 empty] | Students and Staff using advanced software for their learning/teaching and research |  | 500 |  |  | Centre Management
Activity 2: Identify and engage a suitable resource person | Engage suitable resource persons | Suggest suitable software | [14 empty] | 1000
Activity 3: Organise training | Organise training sessions | Suggest resource persons | [14 empty] | 16000
Action 4: DLI 4: Quality of Education/Research
Sub-Action 4a: CEFTER Thematic Annual Research Grant
Activity 1: Hold planning meetings | Hold meetings to plan and send out call for grant applications | [13 empty] | Annual Grant successfully awarded |  | 500 |  |  | Centre Management
Activity 2: Receive and review grant applications | Review grant applications | Review applications | [14 empty] | 1000
Activity 3: Award grants to successful applicants. Target: 6 | Award grants to applicants that meet the set criteria | [15 empty] | 50000
Sub-Action 4b: Funding peer reviewed publications from CEFTER Staff and Students
Activity 1: Students and faculty publications submitted to CEFTER publications committee | Publications by students and faculty submitted to committee for consideration | [13 empty] | Number of publications verified and accepted by Association of African Universities (AAU) monitoring committee |  |  |  |  | Centre Management
Activity 2: The committee reviews and shortlists good quality publications | Select quality publications | [15 empty] | 3000
Activity 3: Shortlisted publications sent to experts for peer review | Selected publications sent for review | [15 empty] | 1000
Activity 4: Payment of publication charges | Payment of publication charges | [15 empty] | 20000
Activity 5: Subscription to Journals | Subscription to Journals | [15 empty] | 4000
Sub-Action 4c: Installations at CEFTER Food Technology Innovation Complex (CEFTIC)
Activity 1: Completion of Construction work at CEFTIC | work ongoing. To be completed | [15 empty] | 282429
Activity 2: Installation of Equipment and Finishing | Supply and installation and testing | [15 empty] | 89538
Activity 3: Intallation of Soughum processing plant | Direct purchase of Soughum plant for research and training | [15 empty] | 50000
Activity 4: Installation of Controlled Atmosphere Facility | Contract awarded for procurement and Installation | [15 empty] | 118032
Activity 5: Develop a testing facility for national and regional companies and registration of CEFTER with Standard regulatory Organisations | Get inputs for the design of the testing facility and registration of CEFTER with Standard regulatory Organisations to be able to certify products | [15 empty] | 10000 |  |  | Centre Management
Sub-Action 4d: Procurement of Laboratory Equipment and Consumables
Activity 1: Conduct needs assesment with departments and partners | Get a comprehensive list of equipments and consumables needed | [13 empty] | Students and Staff enjoying facilities procured for research and teaching
Activity 2: Draft report for consideration | Consider report
Activity 3: Submit Proposal to procurement committee | Submit proposal to procurement committee
Activity 4: Advertise for tenders | Advertise for tenders | [16 empty] | 1600
Activity 5: Procurement of equipment for CEFTER specialised laboratory: Contract awarded for purchase and installation of FITR Spectrometer, power source meter, spray pyrolysis machine, electrochemical workstation, hydrothermal autoclave, spin coater, UHPLC, GCMS, UV-Vis, TEM, XRD, SEM, EDX, Amino Acid Annalizer, Software, informatics ad support to econoetrics laboratory | Award contract | [15 empty] | 460000 |  |  | Centre Management
Sub-Action 4e: Student-Faculty Grant (CPSS)
Activity 1: Students and faculty complete and submit application form | Call for and receive applications for grants from Sudents and Faculty | Submit applications | [12 empty] | Student and Faculty conducting research on approved projects |  |  |  |  | Centre Management
Activity 2: The Scholarship and Grants Committee meets and shortlists candidates for interview | Cosider applications and shortlist candidates for interview | Participate in consideration of applications and shortlisting | [14 empty] | 1000
Activity 3: Shortlisted candidates defend their proposals before the committee | Proposal defence by shortlisted candidates | Proposal defence | [14 empty] | 1000
Activity 4: Disbursement to 10 successful grant applicants | Successful candidates receive disbursement. Target: 5 | [15 empty] | 12000
Sub-Action 4f: Establishment of Regional Research Groups
Activity 1: Conduct needs assesment for establishment of regional working groups | Hold meetings to consider available networking options and advantages | Participate in meetings | [12 empty] | Joint publications in high quality Journals |  | 4000 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Organise a regional faculty stakeholders workshop to formation of regional working groups and how to network. Centre leader to travel and hold strategic meetings | Organise workshops to form regional groups and consider networking options | Participate in workshops | [14 empty] | 34000
Activity 3: Draft reports and share | Draft and share reports | [15 empty] | 2000
Sub-Action 4g: Training on research proposals and publication writing
Activity 1: Prepare report for consideration | The DDR&C to submit report on training for consideration | Participate in meetings | [12 empty] | Publications in high quality Journals |  | 500 |  |  | Centre Management, Regional Partners, Heads of Departments
Activity 2: Identify Facilitators and Benefiaries | Identify and contact facilitators and beneficiaries | Participate in workshops
Activity 3: Implement training | Conduct 2 trainings and organise follow up sessions | [15 empty] | 5000
Sub-Action 4h: International/National Program Accreditation
Activity 1: Undergo national re-accreditation for programs that are due | Certain programs that are due for accreditation will be put up | [15 empty] | 70000
Activity 2: Complete process for full international accreditation | The accreditation process fully implemented
Sub-action 4i: Safeguard activities
Activity 1: Implementation of Gender Based Violence and Sexual Harrassment Policy | Conduct seminars and sensitization campaigns, make billboards. | [15 empty] | 4000 |  |  | Safe Guard Officer
Activity 2: Conduct ESMP implementation audit | Conduct audits for all construction works on campus. | [15 empty] | 5000
Activity 3: Provide work signage around work areas | Provide adequate work signage around work area/institution premises. | [15 empty] | 10000
Activity 4: Implement and administer workers code of conduct | Implement the code of conduct as per ESMP provisions. | [15 empty] | 1000
Action 5: DLI 5: Relevance of Education/Research
Sub-Action 5a: Partnership Activities
Activity 1: Set up an Endowment Fund | Setting up an Endowment fund | Train Staff at MSc and PhD levels | [12 empty] | Completion of agreed activities for each quater |  | 5000 |  |  | Project Technical Committee
Activity 2: Implement partnership activities with the University of Zagreb (Research, Technology Transfer, Incubation, and trainings) | Sign specific agreements with faculties and TTO | Organise internships | [12 empty] | List of partnership activities and collaborations |  | 20000
Activity 3: Establish new partnerships with UNHCR, EU and Morroco | Establish Partnerships | Jiont activities | [12 empty] | Signed MoUs |  | 10000
Activity 4: Meeting with Food processing industries, National policy makers, and NASENI | Development of policies in the food sector, and an effort to woo agic-related industries to the State | [15 empty] | 5000
Sub-Action 5b: Faculty and Students Food Post-harvest Week
Activity 1: Identify crops and assign to students groups | Assign specific crops to student groups | [13 empty] | Students and Entrepreneurs establish businesses using processed food products. Successful patentingof some food products |  | 1000
Activity 2: Assign faculty to student groups as mentor | Assign faculty to each student group to serve as mentor
Activity 3: Student identify food products and prepare budgets | Students prepare and submit budgets
Activity 4: Funding | Funds released for raw materials and accessories for the food week | [15 empty] | 5000
Sub-Action 5c: CEFTER Enterprise Development
Activity 1: Follow up on agro Businesses that were set up previously. | Follow up on startups that received technical and financial awards | [15 empty] | 2000
Activity 2: Developments of Patents and Licencing | Development of patents and licencing | [15 empty] | 2000
Activity 3: Commercialisation of research outputs | Commercialisation of research outputs | [15 empty] | 2000
Activity 4: CEFTER Farms | Cultivation of cassava and some vegetables on the 75 hecter plot of land (in collaboration with BRNADA) | Consider applications | [14 empty] | 10000
Sub-Action 5d: Provision of Extension and Community Awarness on Post-Harvest Losses
Activity 1: Update and review database on agricultural produce | Data will be collected from the field extension staff at regular basis to update the database | Participate in meetings | [12 empty] | Members of the Community adopt improved processing and preservation techniques |  | 1000 |  |  | Centre Management
Activity 3: Training of additional extension workers | In addition to those trained, the Centre will conduct a training to expand on the existing numbers | [15 empty] | 1500
Activity 4: Organise yearly community awareness campaigns | Organise awarenesses campaigns | Engage in campaigns | [14 empty] | 2000 |  |  | CentreManagement
Activity 5: Implementation of the extension service network | Fund and support networks for agricultual extension services | Suggest specific areas and locations | [14 empty] | 10000 |  |  | and Partners
Sub-Action 5e: Student/Staff Internship
Activity 1: Identify Industrial and sectoral Partners for students' internship | Identify the Industries and Sectoral partners that can meet the internship needs | Identify industries and partners
Activity 2: Consider internship areas | Consider the different areas for students internships | Present internship areas | [17 empty] | Centre Management
Activity 3: Develop internship manuals | Develop manuals for internship | Develop manuals | [14 empty] | 1000
Activity 4: Develop Schedule for Student distribution | Prepare a student distribution schedule
Activity 5: Staff Internship | Assign staff to partner institutions to understudy research activities Target 3 | [15 empty] | 10000
Sub-Action 5f: Grant Application:
Activity 1: Hold planning meetings | Hold meetings and consider available grants | Suggest grant winning ideas | [12 empty] | 3 grants applications submitted each year |  | 500 |  |  | Centre Management
Activity 2: Write and apply for grants | Apply for grants | [15 empty] | 500
Activity 3: Hold capacity building on writing for big grants | Engage resource persons to train faculty on application for big grants | Facilitate applications | [14 empty] | 10000
Action 6: DLI 6: Timeliness/Quality of Financial Management
Sub-Action 6a: Regional Project Review Workshops
Activity 1: Identify and notify participants | Identify and notify regional workshop participants | [13 empty] | Management identifying areas of weakness for improvement |  |  |  |  | Centre Management
Activity 2: Prepare update report on project | Prepare update report on project
Activity 3: Submit to CEFTER technical Committee for inputs | Submit report to technical committee for consideration
Activity 4: Travels and accomodation cost | Settle workshop expenses | [15 empty] | 50000
Sub-Action 6b: Internal Monitoring and Evaluation Activities
Activity 1: Conduct quaterly review of all CEFTER activities to ensure they meet desired quality and deadlines | Review CEFTER activities quaterly | [15 empty] | 5000 |  |  | M&E team
Sub-Action 6c: Financial Management
Activity 1: Meeting of Audit committee | The audit committee meets to consider financial reports | [15 empty] | 1500 |  |  | Audit Committee
Activity 2: Training of account/audit staff | Account/Audit staff shall attend annual trainings and workshops | [15 empty] | 10000 |  |  | Centre Management
Activity 3: Purchase and update of accounting software | Payment for licences and upgrade of software | [15 empty] | 3000 |  |  | Accounts Unit
Activity 4: External Audit | External audit of financial reports | [15 empty] | 5000 |  |  | External Auditor
Action 7: DLI : Institutional Impact
Sub-Action 7a: International Institutional Accreditation
Activity 1: Follow up on process for full international Institutional accreditation | The institution will undergo international accreditation with the approved accrediting body following the completion of the self evaluation/gap assesment. | [15 empty] | 1000
Sub-Action 7b: Institutional benchmarking activities (PASET)
Activity 1: Meeting milestones for promoting institutional Impact as outlined in Implimentation Plan | [14 empty] | A completed survey indicating progress to the intervention plan and readiness to participate in benchmarking exercise |  | 5000 |  |  | Centre Management
Sub-Action 7c: ICT Services for innovation in teaching and research
Activity 1: Subscription to NgREN and maintenance of LMS | Annual subscription and mentenance of LMS installations for the University | [15 empty] | 100000 |  |  | Centre Management
Action 8: Communication
Activity 1: Regular Website updates | The website will carry updated information on all Centre activities including research, trainings, awards, and so on. | [13 empty] | Active website links |  | 2000 |  |  | Centre management, Communications officer
Activity 2: Regular update of social media platforms | [14 empty] | Minimum of 3 posts weekly |  | 1000
Activity 3: Online repository for research outputs | Communicate the research outputs of studies conducted by the centres and make it easy for stakeholders to access them. | [13 empty] | Visible page/ tab on centre’s website outlining the various research undertaken by the centre. |  | 1000
Activity 4: Media engagement | Engage mainstream media (radio, televisions, news papers and magazines) to further disseminate centre’s output/ success stories- sharing compelling articles with local and international media. Use community media for grassroots engagement and participation. | [13 empty] | At least 1 mainstream feature quarterly |  | 8000
Activity 5: Production of communication materials- newsletters, brochures, factsheets, infographics, videos, engaging images (photo repository/image bank) | Produce newsletters and magazines. Theatre arts and mass communication departments will be engaged to produce TV and radio jingles that highlight success stories, key activities, and events of the centre in various local languages. They will also be at the forefront of descemination of information. Produce simple communication materials such as brochures and factsheets. | [13 empty] | Production of quarterly newsletters |  | 3000
Activity 6: Produce and Circulate flyers, Posters and Monographs | [16 empty] | 1000
[15 empty] | TOTAL |  | 1685999
[16 empty] | Total Estimated Budget ($) | 1685999